## WORKS AND GOODS
| REPUBLIKA HRVATSKA | REPUBLIC OF CROATIA
| PROJEKT Kontrole onečišćenja okoliša Jadranskog mora (I) | ASEP Control Project (I)
| DAROVNICA BROJ TF017706 | GRANT NUMBER TF017706
| PLAN NABAVE RADOVA I ROBE | PROCUREMENT OF WORKS AND GOODS
| 26.04.2018. | April 26th 2018
Broj projekta / Project Identification No |  | Nabava / Procurement |  |  | Natječajni dokument / Bidding Document |  | Datum objave natječaja / Advertise Bid Date | Natječajna procedura / Bidding Procedure |  | Ocjena ponuda / Bid Evaluation |  | Ugovor / Contract |  |  | Izvoditelj (naziv, adresa) / Contractor (name, address) | Comments
|  | Način nabave / Procurement Method | Revizija svjetske banke / WB revision | Predkvalifikacija / Prequalification | Datum slanja dokumenta na odobrenje / Request for approval of Bidding Document | Odobrenje WB / WB no-objection obtained |  | Datum izdavanja / Issuing of Bidding Document | Predaja i otvaranje ponuda / Submitting and Opening of the Bids | Datum slanja izvješća / Report date | Odobrenje WB / WB no-objection obtained | Objava dodjele ugovora / Notify for Award of Contract | Datum ugovaranja / Contract signed | Završetak posla / Contract completion date
1 |  | 4 | 5 | 6 | 7 | 8 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 27
W/1 | Works on remediation of landfill Sitnica with closed leachate system | ICB | prior |  | 10/05/17 | 30/05/17 | 06/06/17 | 06/06/17 | 08/08/17 | 21/08/17 | 23/08/17 | 24/09/17 | 17/10/17 | 6/11/20* | G.T. TRADE d.o.o. Split | *12 month + 24 month DLP. Funds are increased and realocated from G/1
G/1 | Equipment for monitoring. | NCB | post |  | 05/18 | 05/18 | 05/18 | 05/18 | 06/18 |  |  | 07/18 |  | 10/18 |  | Funds are decreased and realocated to W/1
U POSTUPKU NABAVE / PROCUREMENT PROCEDURE ONGOING
PROVEDBA UGOVORA U TIJEKU / CONTRACT UNDER RUNNING
DOVRSENO / FINISHED

## CONSULTANTS SERVICES
| REPUBLIKA HRVATSKA | REPUBLIC OF CROATIA
| PROJEKT Kontrole onečišćenja okoliša Jadranskog mora (I) | ASEP Control Project (I)
| DAROVNICA BROJ TF017706 | GRANT NUMBER TF017706
| PLAN NABAVE USLUGA | PROCUREMENT OF SERVICES
| 26.04.2018. | April 26th 2018
|  | Nabava / Procurement |  |  | Projektni zadatak / ToR |  | Predkvalifikacija / Prequalification |  |  |  |  | Natječajna procedura / Bidding Procedure |  | Ocjena ponuda / Bid Evaluation |  | Ugovor / Contract |  |  | Konzultant (naziv, adresa) / Consultant (name, address) | comments
[7 empty] | Iskazivanje interesa / Expression of Interest |  |  | Kratka lista kvalificiranih izvođača / Short List
|  | Način nabave / Procurement Method | Revizija svjetske banke / WB revision | Predkvalifikacija / Prequalification | Datum slanja dokumenta na odobrenje / Request for approval of ToR | Odobrenje WB / WB no-objection obtained | Slanje oglasa banci / Sending notice to WB | Datum objave oglasa / Advertise notice date | Datum dostave ponude / Submitting of the expressions | Datum slanja kvalificirane liste na odobrenje / Request for approval of Short List | Odobrenje WB / WB no-objection obtained | Datum izdavanja / Issuing of RFP | Predaja i otvaranje ponuda / Submitting and Opening of the Proposals | Datum slanja izvješća / Report date | Odobrenje WB / WB no-objection obtained | Objava dodjele ugovora / Notify for Award of Contract | Datum ugovaranja / Contract signed | Završetak posla / Contract completion date
|  | 4 | 5 | 6 |  | 8 | 9 | 10 | 11 | 12 | 13 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 26
1$=6,78kn
Technical assistance
TA/1-1 | Preparation of the Feasibility study (FS) with Cost-benefit analysis (CBA), employer’s requirements, conceptual design with location permit and application for EU co-financing of remediation Diklo landfill with leachate capture and leachate treatment plant | QCBS | prior |  | 19/11/14 | 18/12/14 | 19/11/14 | 20/11/14 | 02/12/14 | 18/12/14 | 29/01/15 | 30/01/15 | 09/03/15 | 15/05/15 | 01/06/15 | 12/06/15 | 03/06/15 | 07/17 | JV: SAFEGE Consulting Engineeers, Institut IGH d.d., PanGeo Projekt d.o.o., SAFEGE d.o.o., CONSEKO-SAFEGE S.A. |  | #REF!
TA/1-2 | Updating the EIA with public consultation and dissemination process including control investigation works and monitoring for Diklo landfill | CQS | prior |  | 15/12/14 | 22/12/14 | 22/12/14 | 23/12/14 | 19/01/15 | 06/02/15 | 13/02/16 | 16/02/15 | 17/03/15 | 15/05/15 | 01/06/15 | 12/06/15 | 03/06/15 | 11/16 | Dvokut ECRO ltd. |  | #REF!
TA/2 | Preparation of the Strategic Environmental Assessment (SEA) of the Croatia Waste and Leachate Management Plan and Guidelines for preparation of Waste and Leachate Management Plans | QCBS | prior |  | 28/05/13 | 17/07/13 | 22/12/15 | 09/07/13 | 26/07/13 | 02/08/13 | 12/08/13 | 19/08/13 | 07/01/14 | 25/03/14 | 26/03/14 | 02/04/14 | 31/03/14 | 10/15 | JV: SAFEGE Consulting Engineeers, ENVECO S.A.,K ACTIMAR,CER, SAFEGE d.o.o. | Invoices were issued in EUR with equivalent converted in HRK on the middle currency exchange rate of CNB at the date of issuing invoices. Possibility of signing the new contract with the same Consultant in the amount of around 10% of the basic contract (SSS). | #REF!
TA/2-1 | ASEPC I – Update of Strategic Environmental Assessment of the Croatia Waste and Leachate Management Plan | SSS | prior |  | 05/05/16 | 19/05/16 | [5 empty] | 19/05/16 | 24/05/16 | 25/5/16 | 2/6/16 | 8/6/16 | 03/06/16 | 03/08/16 | JV: SAFEGE SAS and SAFEGE d.o.o.
TA/3-1 | Analysis of the environmental measures and EMP for the remediation of Landfill Sitnica with assessment of nutrient contribution | CQS | post |  | 26/7/2016 | 3/10/2016 | 06/10/2016 | 06/10/2016 | 27/10/2016 |  |  | 17/11/2017 | 19/12/2016 |  |  | 23/01/2017 | 16/01/2017 | 07/02/19 | JV Dvokut EcroLtd- Bioinstitut Ltd. |  | 05/16
TA/3-2 | Preparation of Main Design with Bill of Quantities and TOR for works contract for remediation of landfill Sitnica with closed leachate system | SSS | prior |  | 03/04/16; 21/04/2016 | 26/04/16 | [5 empty] | 04/05/16 | 18/05/16 | 20/06/16 | 20/06/16 | 18/08/16 | 02/08/16 | 06/17 | Hidroplan d.o.o.
TA/3-3 | Supervision Services for remediation of landfill Sitnica | CQS | post |  | 30/08/17 | 04/09/17 | 05/09/17 | 06/09/17 | 25/09/17 |  |  | 28/09/17 | 06/10/17 | 24/10/17 |  | 25/10/17 | 17/10/17 | 06/12/20 | GEOPROJEKT d.d. Split | *13 month + 24 month DLP
U POSTUPKU NABAVE / PROCUREMENT PROCEDURE ONGOING
PROVEDBA UGOVORA U TIJEKU / CONTRACT UNDER RUNNING
DOVRSENO / FINISHED

## GOVERNMENT FINANCED TA
REPUBLIKA HRVATSKA |  |  | REPUBLIC OF CROATIA
PROJEKT Kontrole onečišćenja okoliša Jadranskog mora (I) |  |  | ASEP Control Project (I)
DAROVNICA BROJ TF017706 |  |  | GRANT NUMBER TF017706
PLAN NABAVE USLUGA |  |  | PROCUREMENT OF SERVICES
26.04. 2018. |  |  | April 26th 2018
Za razdoblje od 30.05.2014. do kraja 2018. godine / For the period from 30.05.2014 till the end of the year 2018
| Naziv projekta i lokacija Name and location | Opis dokumentacije Description of documentation | Konzultant (naziv, adresa) / Consultant (name, address) | Status pripreme Current status
ZADAR COUNTY
1 | WMC Biljane Donje - Zadar | Investment proposal package for EU funding for establishment of Waste Management Centre (WMC) "Biljane Donje"in Zadar County 1)Feasibility Study and application with all annexes 2) Waste analysis for WMC FS and project documentation for transfer stations - EIA screening elaborates, Conceptional and Main Designs | 1.) Ars Vivax Ltd. (584.375 HRK) 2) JV - IPZ Uniprojekt TERRA, Hidroing, OIKON (1.010.000 HRK) | documentation completed, project approved for EU funding, Grant Agreement signed on 21 November 2016
ŠIBENIK-KNIN COUNTY
2 | WMC Bikarac | Investment proposal package for EU funding for establishment of Waste Management Centre (WMC) "Bikarac"in Šibenik- Knin County (EIA Study, Waste analysis, Conceptual Design, Feasibility Study and application with all annexes, tender documents) | Consortium: ECOINA d.o.o.,EKONERG d.o.o., Institut IGH d.d., ELEKTROPROJEKT d.d., IUT Ingenieurgemeinschaft Innovative Umwelttechnik GmbH | documentation completed, project approved for EU funding, Grant Agreement signed on 30 October 2015
SPLIT-DALMATIA COUNTY
3 | WMC Lećevica | Investment proposal package for EU funding for establishment of Waste Management Centre (WMC) "Lećevica"in Split-Dalmatia County 1) Waste analysis,FS, EIA summary, Conceptual design, Application with all annexes for WMC 2) Conceptual design for (6)TS, Tender documents with employers requirements for WMC and TS 3) Enviromental protection studies for (6)TS and WMC (for screening process) 4) Study for photovoltaic power plant as part of WMC | 1. JV Procurator Vastitatis Ltd/Enviroplan S.A./Brodarski institut Ltd (4.903.000 HRK + VAT) 2. IPZ Uniprojekt Terra Ltd (3.930.000,00 HRK + VAT) 3. Hudec plan Ltd (164.000 HRK+ VAT) 4. Fractal Ltd (145.000 HRK+ VAT) | project documentation in the final phase of preparation, expected to be completed by the end of ASEPC I. Project
DUBROVNIK-NERETVA COUNTY
4 | WMC Lučino Razdolje | Investment proposal package for EU funding for establishment of Waste Management Centre (WMC) "Lučino Razdolje" in Dubrovnik-Neretva County: 1) Feasibility Study and application with all annexes 2) Conceptual desing for WMC 3) Conceptual desing, main design for TS | 1. JV Procurator Vastitatis Ltd/Enviroplan S.A./Brodarski institut Ltd (2.450.000 HRK + VAT) 2. Hidroplan Ltd (629.300,00 HRK + VAT) 3. JV Hidroplan Ltd/Vita projekt Ltd (685.800 HRK+ VAT) | project documentation in the final phase of preparation, expected to be completed by the end of ASEPC I. Project
PRIMORSKO-GORANSKA COUNTY
5 | Hot spot Sovjak in Viškovo | Investment proposal package for EU funding for remediation/clean-up of hot spot "Sovjak" in Municipality of Viškovo 1.) Investigation Works and EIA Study 2.) EIA Review and Qualitative Risk Assesment 3) Feasibility Study and application with all annexes 4.) Update of the Conceptual Design 5.) Geodethic Survey | 1.) OIKON d.o.o. (934.998,75 HRK) 2.) Blue Wet d.o.o. (195.000 HRK + VAT) 3.) Izvan kruga d.o.o. (188.000 HRK + VAT) 4.) IPZ Uniprojekt TERRA d.o.o. (23.625 HRK) 5.) Geo Mreža d.o.o. (18.500 HRK) | documentation completed, call for proposals for EU funding in expected to be launched soon
COUNTY OF ISTRIA
6 | Remediation of landfill - Donji Picudo East in Umag | Investment proposal package for EU funding for remediation of landfill "Donji Picudo - East" in Umag 1) application form with needed annexes, tender documentation 2) Main Design | 1) JHP Projektne rešitve d.o.o. 2) IPZ Uniprojekt TERRA d.o.o. | documentation completed, project approved for EU funding, project successfully implemented by December 2016